## Sheet1
№ | Topic | Deadline | Executor | Comments
1 | FEASIBILITY
A | Stakeholder analysis |  | Michele&Pierluigi |  | delay
1.1 | Description Matrix |  | P&M |  | completed
1.2 | SWOT analysis |  | A&CH |  | on process
1.3 | Spider Diagram |  | B
1.4 | Venn Diagram |  | B
1.5 | Survey |  | A&CH
B | Problem Analysis |  | Arianna&Chiara
2.1 | Problem tree |  | A&CH
C | Objectives Analysis |  | Bobur
3.1 | Solution tree |  | A&CH
D | Strategy selection |  | Bobur
4.1 | Results identification for the investment
E | Work-plan specification |  | I will ask form professor
5.1 | Specific feasibility study
5.2 | System analysis
5.3 | Design
5.4 | Implementation
5.5 | Monitoring and assessment
2 | Development Life Cycle
a | Specific Feasibility study | 22.11.2019 | Arianna&Chiara
b | System Analysis | 22.11.2019 | Michele&Pierluigi&Bobur
c | Design (UML: Cases diagram, Class, Sequence Activity) | 13.12.2019 | Arianna&Chiara&Bobur&Michele
d | Implementation (UML, Python SQL...) |  | Saidbek&Pierluigi
e | operation prototype |  | Saidbek&Pierluigi
f | Dissemination |  | All
g | Monitoring and assessment |  | I will ask form professor
10 minutes video
3 minuts kickstar